Project Plan – Digital Service Report Application

Project Objective

Develop a simple digital application to replace the current MS Word one-page report form. The application should work on both desktop and mobile devices and allow users to complete reports using dropdown menus and standard form fields.

Phase 1 – Requirements & Planning

Estimated Time: 2–5 days

| TASK | STATUS | COMPLETE |
| --- | --- | --- |
| Review of existing Word Document |  |  |
| Identify all required fields |  |  |
| Determine: - Required dropdown lists - Required text fields - Mandatory vs optional field |  |  |
| Define desired output: - PDF export - Email submission - Database storage |  |  |
| Confirm desktop and mobile requirements |  |  |
| Create simple wireframe/mockup |  |  |
| Deliverables: - Approved requirements list - Draft screen layout/wireframe - Finalized scope for Version 1 |  |  |

Phase 2 – Front-End Development

Estimated Time: 1–2 weeks

| TASK | STATUS | COMPLETE |
| --- | --- | --- |
| Create responsive form layout |  |  |
| Build: - Dropdown menus - Text fields - Date fields - Checkboxes (if needed) |  |  |
| Add basic validation |  |  |
| Optimize layout for: - Desktop - Tablet - Mobile Devices |  |  |
| Deliverables: - Functional front-end form - Mobile-friendly interface - Initial user testing version |  |  |

Phase 3 – Backend / Data Handling

Estimated Time: 1–2 weeks

| TASK | STATUS | COMPLETE |
| --- | --- | --- |
| Configure simple backend platform - Example: Firebase, Supabase, or Power Apps |  |  |
| Set up data storage |  |  |
| Connect form submissions to backend |  |  |
| Deliverables: - Working submission process - Stored form data - PDF/email functionality |  |  |

Phase 4 – Testing & Revisions

Estimated Time: 3–5 days

| TASK | STATUS | COMPLETE |
| --- | --- | --- |
| Test on: - Desktop browsers - Mobile devices |  |  |
| Verify: - Dropdown functionality - Form validation - PDF formatting - Data saving |  |  |
| Correct bugs/issues |  |  |
| Gather user feedback |  |  |
| Deliverables: - Finalized application - Corrected issues - Approved production version |  |  |

Phase 5 – Deployment & Training

Estimated Time: 1–3 days

| TASK | STATUS | COMPLETE |
| --- | --- | --- |
| Deploy application |  |  |
| Create simple user instructions |  |  |
| Train internal users |  |  |
| Establish support/update process |  |  |
| Deliverables: - Live application - User guide - Support documentation |  |  |

Estimated Total Timeline

| PHASE | ESTIMATED DURATION |
| --- | --- |
| Planning and Requirements | 2-5 days |
| Front End Development | 1-2 weeks |
| Backend/Data Handling | 1-2 weeks |
| Testing and Revisions | 3-5 days |
| Deployment and Training | 1-3 days |
| Total Estimated Project Duration: | 3-6 weeks |